## Feature_Tiers
Feature | Definition / Purpose | Tier (MVP/Core/Stretch) | Size (S/M/L) | Owner | Dependencies | Notes
Base Sanctuary Hub | Primary scene where ghosts, buildings, and core interactions live. | MVP | L | Design/Code | Scenes, Prefabs, Input
Player Controller & Camera | Move, interact (feed, clean, repair), target selection; camera framing. | MVP | M | Code | Input, HUD
Save/Load v1 | Persist player, ghosts, resources, time, buildings. | MVP | M | Code | Serialize Table
Appetite System | Ghost hunger; Offerings/Ectofruit restore. | MVP | M | Code/Design | Garden, Inventory
Contentment System | Global mood; controls Essence, Unrest, Mementos. | MVP | M | Code/Design | HUD, Ghosts
Essence Generation | Happy ghosts passively generate Essence over time. | MVP | S | Code | Contentment
Manifest System | Ghost sickness; leaves ectoplasm that reduces mood. | MVP | M | Code/Design | SFX, VFX, Cleaning
Cleaning System | Player cleans ectoplasm; janitor support later. | MVP | S | Code | Manifest
Repair System | Fix vandalized/damaged structures with Timber/Rock. | MVP | S | Code | Inventory
Inventory & Resources | Track Tokens, Essence, Remains, Ectoplasm, Timber, Rock. | MVP | S | Code | HUD
Garden of Rest (Basic) | Place 1–2 plots; plant flower; fertilize; harvest Offering/Ectofruit. | MVP | M | Design/Code | Plants SOs, VFX
Offerings Feeding | Feed ghost to restore Appetite. | MVP | S | Code | Inventory, UI
Altar – Cleansing Ritual | Consume Essence + Remains to cure Manifest globally. | MVP | M | Design/Code | Rituals SO
Grace Earn/Spend Loop (Stub) | Earn Grace from ritual; spend to unlock Garden/Altar upgrades. | MVP | M | Design/Code | Upgrade Tree
Mementos Generation | High average Contentment creates Mementos for dungeon access. | MVP | S | Code/Design | Contentment
Shard Gate | Consume Memento to enter a Shard. | MVP | S | Code | Scenes, UI
Shard Run (Stub) | Short run; 1 enemy type; collect Essence/Remains; exit. | MVP | L | Design/Code | Combat, Loot
Dungeon Loot Return | Convert pickups into resources on return. | MVP | S | Code | Inventory
HUD & Toasts | Meters (Appetite, Contentment, Essence) + pickup toasts. | MVP | M | UI/Code | Fonts, Icons
Basic Audio Pass | Ambient loop + core SFX clicks/clean/feed. | MVP | S | Audio | Mix
Ghost Spawning/Binding | Bind rescued ghosts to base via Altar. | Core | M | Design/Code | Rituals, UI
Temperament System | Mournful, Trickster, Spiteful, Cold, Bright, etc. | Core | M | Design/Code | Ghost AI, Contentment
Bond System | Per-ghost relationship levels; affects reliability and buffs. | Core | M | Design/Code | UI, Requests
Follower Tasks | Assign Janitor, Gardener, Builder, Alchemist, Ritual Assistant. | Core | M | Design/Code | Stations, UI
Requests System | Per-ghost personal quests that impact Bond and mood. | Core | M | Design/Code | Dialogue/UI
Unrest Events | Low mood triggers vandalism, hauntings, garden destruction. | Core | M | Design/Code | VFX/SFX
Afflictions & Warded Chamber | Severe breakdowns requiring rest/healing. | Core | M | Design/Code | Rituals
Building Placement | Place/move buildings on grid with snap & collision. | Core | M | Design/Code | Prefabs, UI
Building Upgrades | Upgrade level for Altar, Garden, Workshop, etc. | Core | M | Design/Code | Grace Tree
Sawmill & Quarry | Passive Timber/Rock production with assigned ghosts. | Core | M | Design/Code | Tasks
Workshop Refining | Timber→Boards, Rock→Bricks queues; follower work. | Core | M | Design/Code | Stations UI
Alchemy Table | Brew potions from Essence + Ectoplasm + Remains + Herbs. | Core | L | Design/Code | Garden, Recipes
Potion Categories | Restoration, Protection, Utility, Empowerment, Social. | Core | M | Design/Code | Alchemy
Relic Forge | Combine Relic Fragments into Charms. | Core | M | Design/Code | Dungeon Bosses
Charms System | Equip to ghosts; modify mood decay, appetite, unrest. | Core | M | Design/Code | Relic Forge, UI
Altar – Release Ritual | Peaceful send-off → Grace + Memoria + Mementos. | Core | M | Design/Code | Cutscene hooks
Altar – Feast Ritual | Group Appetite/Contentment boost. | Core | M | Design/Code | Audio/VFX
Altar – Binding Ceremony | Anchor new ghost (recruit from shard). | Core | M | Design/Code | Shard Rescue
Shard Biome 01 – Withered Parish | Core dungeon with rooms, wraiths, anchors. | Core | L | Design/Code | Loot, Boss
Elite Enemy Variant | Harder enemy type with better drops. | Core | M | Design/Code | Combat
Boss 01 | First major memory boss; drops Relic Fragments. | Core | L | Design/Code | Audio/VFX
Companion Ghost System | Bring one ghost; temperament grants passive bonus. | Core | M | Design/Code | UI, Followers
Echo Puzzles (Basic) | Simple interactables to open paths or reduce corruption. | Core | M | Design/Code | Loot
Inventory Panel | Resources list, categories, tooltips. | Core | M | UI/Code | Icons
Followers Panel | Ghost list, detail view, assign tasks, equip charms. | Core | M | UI/Code | Ghost Data
Rituals Panel | Select ritual, show costs/cooldowns. | Core | M | UI/Code | Altar
Garden Panel | Plant, fertilize, harvest; plot overview. | Core | M | UI/Code | Plants
Requests Panel | Track active requests and rewards. | Core | M | UI/Code | Requests
Settings Menu | Audio, controls, accessibility settings. | Core | S | UI/Code
Save Slots UI | Three slots; delete/confirm UI. | Core | S | UI/Code | Save/Load
Controller Glyphs | Dynamic input icons (KB/M, gamepad). | Core | S | UI/Code | Input
Ambient Zones | Hub/day/night ambiences, shard ambiences. | Core | M | Audio | Mix Snapshots
VFX Pack 1 | Core VFX for Manifest, Rituals, Garden, Combat. | Core | M | VFX | Shaders
Save/Load v2 | Broader schema; queues, ritual history, decor. | Core | M | Code | Serialize Table
Autosave Rules | At dawn, post-ritual, post-dungeon, pre-quit. | Core | S | Code | Save System
Localization Hooks | String tables & font fallbacks; en-US first. | Core | M | UI/Code | Localization
Shard Biome 02 – Dream Trenches | Second dungeon theme; new enemies & boss. | Stretch | L | Design/Code | Art/Audio
Shard Biome 03 – Lantern Isles | Third dungeon theme. | Stretch | L | Design/Code
Boss 02 | Second major memory boss. | Stretch | L | Design/Code
Boss 03 | Third major memory boss. | Stretch | L | Design/Code
Event Rooms | Visitors, merchants, side events in shards. | Stretch | M | Design/Code
Doctrine/Philosophy Paths | Kind vs Efficient caretaker branches; alter rituals. | Stretch | L | Design/Code | Rituals
Visitors System | Random souls request help; unique trades. | Stretch | M | Design/Code | Requests
Dream Events | Night visions with small Grace/lore boosts. | Stretch | M | Design/Code | Audio/VFX
Familiar Pet | Companion that cleans or reacts to mood. | Stretch | S | Design/Code | Manifest
Seasonal Decor | Seasonal visuals with small mood perks. | Stretch | M | Art/UI
Advanced Ritual Combos | Stack or sequence rituals for enhanced effects. | Stretch | M | Design/Code | Cooldown System
Potion Side Effects System | Random mishaps if brewed by unhappy alchemists. | Stretch | M | Design/Code | Alchemy
Charm Sets & Synergies | Set bonuses when multiple ghosts wear theme charms. | Stretch | M | Design/Code | Charms
Garden Plant Set 2 | More flowers; unique auras & ectofruit variants. | Stretch | M | Design/Code | Plants
Photo/Memory Album | Released ghosts + quotes/snapshots. | Stretch | M | UI/Code | Memoria
Achievements | In-game or platform trophies. | Stretch | M | Code
Cloud Save | Cross-device saves. | Stretch | M | Code | Platform SDK
Rebindable Controls | Full input remapping UI. | Stretch | M | UI/Code | Input
Advanced Accessibility | Colorblind modes, font scaling per panel. | Stretch | M | UI/Code
Dev Console & Cheats | Spawn items, set mood, toggle systems. | Stretch | S | Code
Profiler Markers | Custom markers for frame budgeting. | Stretch | S | Code
Automated Build Pipeline | CI builds per branch, version stamping. | Stretch | M | Tech

## Dependencies_Graph
Feature | Tier | Depends On | Critical Path
Base Sanctuary Hub | MVP |  | YES
Player Controller & Camera | MVP
Save/Load v1 | MVP
Appetite System | MVP
Contentment System | MVP
Essence Generation | MVP
Manifest System | MVP
Cleaning System | MVP
Repair System | MVP
Inventory & Resources | MVP
Garden of Rest (Basic) | MVP
Offerings Feeding | MVP
Altar – Cleansing Ritual | MVP
Grace Earn/Spend Loop (Stub) | MVP
Mementos Generation | MVP
Shard Gate | MVP
Shard Run (Stub) | MVP
Dungeon Loot Return | MVP
HUD & Toasts | MVP
Basic Audio Pass | MVP
Ghost Spawning/Binding | Core
Temperament System | Core
Bond System | Core
Follower Tasks | Core
Requests System | Core
Unrest Events | Core
Afflictions & Warded Chamber | Core
Building Placement | Core
Building Upgrades | Core
Sawmill & Quarry | Core
Workshop Refining | Core
Alchemy Table | Core
Potion Categories | Core
Relic Forge | Core
Charms System | Core
Altar – Release Ritual | Core
Altar – Feast Ritual | Core
Altar – Binding Ceremony | Core
Shard Biome 01 – Withered Parish | Core
Elite Enemy Variant | Core
Boss 01 | Core
Companion Ghost System | Core
Echo Puzzles (Basic) | Core
Inventory Panel | Core
Followers Panel | Core
Rituals Panel | Core
Garden Panel | Core
Requests Panel | Core
Settings Menu | Core
Save Slots UI | Core
Controller Glyphs | Core
Ambient Zones | Core
VFX Pack 1 | Core
Save/Load v2 | Core
Autosave Rules | Core
Localization Hooks | Core
Shard Biome 02 – Dream Trenches | Stretch
Shard Biome 03 – Lantern Isles | Stretch
Boss 02 | Stretch
Boss 03 | Stretch
Event Rooms | Stretch
Doctrine/Philosophy Paths | Stretch
Visitors System | Stretch
Dream Events | Stretch
Familiar Pet | Stretch
Seasonal Decor | Stretch
Advanced Ritual Combos | Stretch
Potion Side Effects System | Stretch
Charm Sets & Synergies | Stretch
Garden Plant Set 2 | Stretch
Photo/Memory Album | Stretch
Achievements | Stretch
Cloud Save | Stretch
Rebindable Controls | Stretch
Advanced Accessibility | Stretch
Dev Console & Cheats | Stretch
Profiler Markers | Stretch
Automated Build Pipeline | Stretch

## Sprint_Planner
Feature | Tier | Size | Est. Weeks | Start Week | End Week
Base Sanctuary Hub | MVP | L | 3 | 0 | 3
Player Controller & Camera | MVP | M | 1.5 | 3 | 4.5
Save/Load v1 | MVP | M | 1.5 | 4.5 | 6
Appetite System | MVP | M | 1.5 | 6 | 7.5
Contentment System | MVP | M | 1.5 | 7.5 | 9
Essence Generation | MVP | S | 0.5 | 9 | 9.5
Manifest System | MVP | M | 1.5 | 9.5 | 11
Cleaning System | MVP | S | 0.5 | 11 | 11.5
Repair System | MVP | S | 0.5 | 11.5 | 12
Inventory & Resources | MVP | S | 0.5 | 12 | 12.5
Garden of Rest (Basic) | MVP | M | 1.5 | 12.5 | 14
Offerings Feeding | MVP | S | 0.5 | 14 | 14.5
Altar – Cleansing Ritual | MVP | M | 1.5 | 14.5 | 16
Grace Earn/Spend Loop (Stub) | MVP | M | 1.5 | 16 | 17.5
Mementos Generation | MVP | S | 0.5 | 17.5 | 18
Shard Gate | MVP | S | 0.5 | 18 | 18.5
Shard Run (Stub) | MVP | L | 3 | 18.5 | 21.5
Dungeon Loot Return | MVP | S | 0.5 | 21.5 | 22
HUD & Toasts | MVP | M | 1.5 | 22 | 23.5
Basic Audio Pass | MVP | S | 0.5 | 23.5 | 24
Ghost Spawning/Binding | Core | M | 1.5 | 24 | 25.5
Temperament System | Core | M | 1.5 | 25.5 | 27
Bond System | Core | M | 1.5 | 27 | 28.5
Follower Tasks | Core | M | 1.5 | 28.5 | 30
Requests System | Core | M | 1.5 | 30 | 31.5
Unrest Events | Core | M | 1.5 | 31.5 | 33
Afflictions & Warded Chamber | Core | M | 1.5 | 33 | 34.5
Building Placement | Core | M | 1.5 | 34.5 | 36
Building Upgrades | Core | M | 1.5 | 36 | 37.5
Sawmill & Quarry | Core | M | 1.5 | 37.5 | 39
Workshop Refining | Core | M | 1.5 | 39 | 40.5
Alchemy Table | Core | L | 3 | 40.5 | 43.5
Potion Categories | Core | M | 1.5 | 43.5 | 45
Relic Forge | Core | M | 1.5 | 45 | 46.5
Charms System | Core | M | 1.5 | 46.5 | 48
Altar – Release Ritual | Core | M | 1.5 | 48 | 49.5
Altar – Feast Ritual | Core | M | 1.5 | 49.5 | 51
Altar – Binding Ceremony | Core | M | 1.5 | 51 | 52.5
Shard Biome 01 – Withered Parish | Core | L | 3 | 52.5 | 55.5
Elite Enemy Variant | Core | M | 1.5 | 55.5 | 57
Boss 01 | Core | L | 3 | 57 | 60
Companion Ghost System | Core | M | 1.5 | 60 | 61.5
Echo Puzzles (Basic) | Core | M | 1.5 | 61.5 | 63
Inventory Panel | Core | M | 1.5 | 63 | 64.5
Followers Panel | Core | M | 1.5 | 64.5 | 66
Rituals Panel | Core | M | 1.5 | 66 | 67.5
Garden Panel | Core | M | 1.5 | 67.5 | 69
Requests Panel | Core | M | 1.5 | 69 | 70.5
Settings Menu | Core | S | 0.5 | 70.5 | 71
Save Slots UI | Core | S | 0.5 | 71 | 71.5
Controller Glyphs | Core | S | 0.5 | 71.5 | 72
Ambient Zones | Core | M | 1.5 | 72 | 73.5
VFX Pack 1 | Core | M | 1.5 | 73.5 | 75
Save/Load v2 | Core | M | 1.5 | 75 | 76.5
Autosave Rules | Core | S | 0.5 | 76.5 | 77
Localization Hooks | Core | M | 1.5 | 77 | 78.5
Shard Biome 02 – Dream Trenches | Stretch | L | 3 | 78.5 | 81.5
Shard Biome 03 – Lantern Isles | Stretch | L | 3 | 81.5 | 84.5
Boss 02 | Stretch | L | 3 | 84.5 | 87.5
Boss 03 | Stretch | L | 3 | 87.5 | 90.5
Event Rooms | Stretch | M | 1.5 | 90.5 | 92
Doctrine/Philosophy Paths | Stretch | L | 3 | 92 | 95
Visitors System | Stretch | M | 1.5 | 95 | 96.5
Dream Events | Stretch | M | 1.5 | 96.5 | 98
Familiar Pet | Stretch | S | 0.5 | 98 | 98.5
Seasonal Decor | Stretch | M | 1.5 | 98.5 | 100
Advanced Ritual Combos | Stretch | M | 1.5 | 100 | 101.5
Potion Side Effects System | Stretch | M | 1.5 | 101.5 | 103
Charm Sets & Synergies | Stretch | M | 1.5 | 103 | 104.5
Garden Plant Set 2 | Stretch | M | 1.5 | 104.5 | 106
Photo/Memory Album | Stretch | M | 1.5 | 106 | 107.5
Achievements | Stretch | M | 1.5 | 107.5 | 109
Cloud Save | Stretch | M | 1.5 | 109 | 110.5
Rebindable Controls | Stretch | M | 1.5 | 110.5 | 112
Advanced Accessibility | Stretch | M | 1.5 | 112 | 113.5
Dev Console & Cheats | Stretch | S | 0.5 | 113.5 | 114
Profiler Markers | Stretch | S | 0.5 | 114 | 114.5
Automated Build Pipeline | Stretch | M | 1.5 | 114.5 | 116

## Milestones
Milestone | Status | Window (Weeks) | Goal (One-Liner) | Entry Criteria | Exit Criteria (Definition of Done) | Key Deliverables | Dependencies | Risks / Mitigations | Notes
M0 – Foundations Locked | Done | Wk 1–2 (Done) | Vision, systems map, and serialization foundations documented. | Week 1 & 2 docs drafted (Vision, Pillars, Systems Map, Save Table). | Docs reviewed, terminology locked; resource buckets & dependencies mapped. | Week 1 Brief, Systems Map diagrams, Save/Serialize Master. | None | Scope creep in docs → Mitigate with 'Not-to-do' list enforcement. | Reference index file created for ChatGPT access.
M1 – Feature Scoping (Week 3) | Done | Wk 3 (Done) | Tier, size, and dependency clarity for all features. | Feature list compiled; tiers identified. | Feature_Tiers.xlsx approved; critical path highlighted; MVP defined. | Feature_Tiers, Dependencies Graph, Sprint Planner baseline. | M0 | Overscoping MVP → Keep only loop-critical features. | Owner column optional (solo dev).
M2 – Pre-Production Finalization | Planned | Wk 4–5 | Lock Rituals & Altar spec and Tech Bible v0.1, folder conventions, pipelines. | Week 3 accepted; Pipeline_Standards.md saved. | Rituals_And_Altar.md, Requests_System.md, Temperament_System.md finalized. | Ritual spec, Requests/Temperament docs, updated Pipeline_Standards. | M1 | Unclear ritual costs → Prototype small values first. | No sprint planning in milestones.
M3 – MVP Prototype (Playable Loop) | Planned | Wk 6–8 | End-to-end loop functional: care → mementos → shard → ritual → grace. | M2 complete; base scene exists. | Playable build with minimal art; 1 ritual, 1 shard, 1 enemy, 1 ghost type. | MVP scene, basic audio, HUD meters, save v1. | M2 | Feature drift → Freeze MVP feature list; bug triage only. | Target 20–30 min session proving loop fun.
M4 – Vertical Slice | Planned | Wk 9–12 | Representative quality of core systems and tone. | M3 playable; VFX Pack 1; ambient audio stubs. | Companion system, Boss 01, Charms & Potions core, Garden pass. | Slice build with trailer-ready footage areas. | M3 | Perf spikes → Profile; reduce overdraw & GC. | Focus on readability and juice.
M5 – Core Systems Complete | Planned | Wk 13–16 | All Core-tier systems implemented & stable. | Vertical Slice accepted; Feature_Tiers 'Core' green. | Requests, Tasks, Temperaments, Warded Chamber, Building upgrades. | Core content complete, defects manageable. | M4 | System interactions causing edge bugs → Integration tests. | Lock mechanics; no new systems.
M6 – Content Pass 1 | Planned | Wk 17–20 | Add breadth: more plants, potions, charms, events. | Core stable; pipelines active. | Garden Set 2, Potion variants, Event rooms in Shard 01. | Content drop without changing systems. | M5 | Content bloat → Keep values data-driven (SO). | Use balance sheet for drop rates.
M7 – Polish & QoL | Planned | Wk 21–22 | Improve UX, feedback, readability, and accessibility. | Core content tested; feedback gathered. | Controller glyphs, toasts polish, accessibility options, localization hooks. | UX delight and clarity. | M6 | UI scope creep → Small wins, avoid new panels. | Prioritize readability.
M8 – Steam Page & Trailer Update | Planned | Wk 23 | Public-facing materials refreshed. | Vertical slice footage captured. | Updated trailer clips, screenshots, refined capsule art. | Marketing-ready materials. | M4 | Time sink → Limit capture sessions. | Keep game name & tone consistent.
M9 – Beta | Planned | Wk 24–26 | Feature complete; balance & bug-hunting focus. | Core systems closed; content pass 1 in. | Playtest instrumentation, bug triage, balance passes. | Stability and tuning toward launch. | M7 | Community pressure → Scope cuts acceptable. | Define triage rubric.
M10 – Launch Prep | Planned | Wk 27–28 | Release candidate builds & platform compliance. | Beta telemetry and crash reports addressed. | RC builds, platform packaging, store assets finalized. | Ready for release window. | M9 | Submission delays → Prepare buffer. | Checklist-driven go/no-go.
M11 – Post-Launch Patch 1 | Planned | Wk 29 | Fix high-impact bugs and stability issues. | Crash reports & feedback collected. | Patch notes, hotfix build, small QoL changes. | Faster stability and goodwill. | M10 | Unexpected regressions → Keep changes surgical. | No features; only fixes.
M12 – Content Pack 1 | Planned | Wk 30–34 | New biome or event pack to sustain engagement. | Post-launch stability achieved. | Shard Biome 02, new boss, new charms/potions. | Meaningful post-launch content beat. | M11 | Content spike risk → Reuse pipelines & data tables. | Ship as DLC or free update.

## Legend
Status | Color
Done
In Progress
Planned
Milestones are high-level; exclude sprint planning per design.