## Milestone_Tree
Milestone | Duration (Days) | Key Systems | Content Scope | Readiness Criteria
Vertical Slice | 90 | Core Loop (Contentment, Inventory, Save, UI) | 1 Biome + Ritual Loop | Playable loop @30FPS + Harmony tracked
Alpha | 90 | All Systems (Manifest, Requests, Economy) | 3 Biomes + Full UI Pass | Feature complete + stable save/load
Beta | 90 | Balance & Polish | All Art/Audio + Loc Stub | No blockers + <50 open bugs
Release | 90 | QA, Optimization, Localization Final | All Languages + Marketing Build | 95% stability + performance targets met
Post-Launch | — | Events & QoL Updates | New Biome + Seasonal Events | Post-launch patch pipeline ready

## Feature_Mapping
System | File | Assigned Milestone
Contentment / Bond / Grace | Contentment_Bond_Grace_Meta_System_Spec_Dashboard.xlsx | Vertical Slice
Manifest / Contagion | Manifest_Contagion_System_Spec.xlsx | Alpha
Rituals | Rituals_And_Altar_System_Spec_Wired_WithCharts_Sliders_Threshold_Feast.xlsx | Alpha
Adventure / Shards | Adventure_Shards_System_Spec_BiomeDashboard_Risk.xlsx | Alpha
Building / Construction | Building_Construction_System_Spec_Planner_Dashboard.xlsx | Beta
Garden of Rest | Resources_List_With_Folder_Structure_SeedsOutputs_Metrics_WithGlobals.xlsx | Beta
Potions / Alchemy | Potions_System_Spec_With_Metrics.xlsx | Beta
Relics & Charms | Relics_And_Charms_System_Spec_Wired.xlsx | Beta
Followers / Requests | Follower_Tasks_And_Requests_System_Spec_Wired_LiveAndChart.xlsx | Alpha
Resources / Economy | Token_Economy_Model.xlsx | Vertical Slice
Save / Serialization | Save_Serialize_Master_Split_JSON.xlsx | Vertical Slice

## Readiness_Checklist
Milestone | Art | Design | Tech | QA
Vertical Slice | 0 | 1 | 2 | 0
Alpha | 1 | 2 | 3 | 1
Beta | 2 | 2 | 3 | 2
Release | 3 | 3 | 3 | 3
Post-Launch | 3 | 3 | 3 | 3

## Timeline_View
Month | Phase | Key Goals
1-3 | Vertical Slice | Playable core loop
4-6 | Alpha | Feature complete
7-9 | Beta | Balance + polish
10-12 | Release | Final QA + Localization