## Risk_Matrix
Category | Risk | Probability (1-5) | Impact (1-5) | Score (P×I) | Mitigation | Owner
Technical | Async save race condition | 4 | 5 | 20 | Thread-safe queue, autosave locks | Engineer
Design | Player confusion (Unrest loop) | 2 | 4 | 8 | Tutorial overlay, UI clarity | Design Lead
Art | Shader performance on Switch | 3 | 4 | 12 | Fallback URP shaders | Tech Artist
Schedule | Scope creep | 3 | 5 | 15 | Milestone locks + backlog | Producer
People | Solo dev burnout | 5 | 5 | 25 | Timeboxing, rest cycles | You

## Heatmap
Probability | 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25

## Category_Summary
Category | Average Score
Technical | 20
Design | 8
Art | 12
Schedule | 15
People | 25