## Sheet1
System / Feature | Category | Phase | Start (Day) | End (Day) | Dependency | Milestone / Deliverable | Duration (Days)
GameManager & EventBus Core | Framework | Vertical Slice | 1 | 10 | — | Boot managers, event routing online | 10
SaveManager & TimeManager | Framework | Vertical Slice | 11 | 20 | GameManager | Autosave, day/night cycle functional | 10
UIManager Core | Framework | Vertical Slice | 21 | 30 | GameManager | HUD prototype; basic bindings live | 10
SpiritManager & MoodComponent | Gameplay | Vertical Slice | 31 | 50 | Framework | Ghost mood & appetite loops active | 20
InteractionSystem | Gameplay | Vertical Slice | 51 | 65 | SpiritManager | Feed / soothe / clean interactions working | 15
EssenceSystem & Grace Loop | Gameplay | Vertical Slice | 66 | 80 | InteractionSystem | Resource generation & rewards | 15
GardenManager (Garden of Rest) | Economy | Vertical Slice | 81 | 100 | EssenceSystem | Growth & harvest cycles functional | 20
RitualsManager | Systems | Vertical Slice | 101 | 120 | GardenManager | Care & cleansing rituals online | 20
Follower Task System | AI & Systems | Alpha | 121 | 140 | RitualsManager | Ghost roles & productivity loops integrated | 20
Requests System | AI & Systems | Alpha | 141 | 155 | Follower Task System | Randomized favors, dialogue toasts | 15
Dungeon Shard Prototype (AdventureManager) | Gameplay Expansion | Alpha | 156 | 175 | Requests System | Dungeon rooms & relic drops functional | 20
Relics & Charms System | Crafting | Alpha | 176 | 190 | Dungeon Shard | Charm crafting & equipping operational | 15
Potions System (Alchemy Table) | Crafting | Alpha | 191 | 210 | GardenManager | Brew, equip, and use potions; effects applied | 20
Grace & Upgrade Tree | Meta | Alpha | 211 | 225 | Relics & Potions | Upgrades & building unlocks working | 15
Dungeon Boss & Unique Rewards | Gameplay Expansion | Alpha | 226 | 240 | Dungeon Shard | Boss drop table & relic integration | 15
Optimization & Async Save Queue | Technical | Beta | 241 | 260 | Framework | Stable frame timings; async saving implemented | 20
Accessibility & Localization | UX / QA | Beta | 261 | 275 | UIManager | Text scaling, rebinds, CSV localization | 15
Audio Pass & Mix | Audio | Beta | 276 | 290 | All Core Systems | Music & ambience layered, final mix started | 15
Narrative & Dialogue Pass | Writing | Beta | 291 | 305 | Requests System | All ghost dialogue implemented | 15
Closed Beta & QA | QA | Beta | 306 | 330 | All Systems | Testing, bug-fix, and balance pass | 25
Trailer Capture & Press Kit | Marketing | Release | 331 | 345 | QA | Marketing content finalized | 15
Platform Certification & Submission | QA / Release | Release | 346 | 355 | QA | Builds validated & submitted | 10
Launch & Post-Launch Support | Operations | Release | 356 | 365 | Certification | Day-1 patch and analytics integration | 10